## Cover
ISOKO MARKETPLACE
Multi-vendor Marketplace Platform — SIT / UAT Test Pack
Authentication • Catalogue • Cart & Discount • Checkout • Wishlist & Orders • Seller & Admin • Non-functional
Buyer storefront / uat.isoko.rw (UAT)
PROJECT INFORMATION / AMAKURU Y'UMUSHINGA
Project | Isoko Multi-vendor Marketplace (mobile-money-first, escrow)
Application / Module | Web storefront + REST API + database (containerised, Kubernetes)
In-scope journeys | Login/Register, Catalogue, Cart, Discount, Checkout (MoMo/Airtel/Card, escrow), Wishlist, Orders, Seller onboarding & fulfilment, OTP delivery & payout
Out of scope | Native apps; buyer disputes & reviews (Release 2); payment-gateway internals; live MoMo charges; real customer data
Governing SRS | ISK-SRS-2026-001 v1.0 — use cases UC-01..15
Governing Inception | ISK-INC-2026-001 v1.0 — milestones M1–M4, 19-week plan
Test Phase | SIT → UAT
Environment | UAT / staging Kubernetes cluster (seed data: SRS Appendix B)
Build / Release | 1.0-rc
Test Lead | QA lead (rotating) · Trainer: [Trainer name]
Business Owner / PO | Isoko Product Owner
UAT window | Session 1: Week 12 · Session 2: Week 16 · Sign-off: Milestone 4 (Week 19)
Document ID / Version | ISK-UAT-2026-001 · v1.0 · 30 September 2026
HOW TO USE / UBURYO BWO GUKORESHA
1. Confirm entry criteria | SRS baselined, Inception accepted, smoke test (home + /healthz) green, Appendix B seed loaded. Do not start if smoke fails.
2. Pick a test sheet | Authentication, Catalogue, Cart & Discount, Checkout, Wishlist & Orders, Seller & Admin, or Non-functional.
3. Run each test case | Follow Test Steps on the UAT storefront (or API notes where marked). Record Actual Result.
4. Record the outcome | Status dropdown: Pass / Fail / Blocked / Not Executed. Failures get a Defect ID.
5. Watch the Dashboard | Counts and pass rate update live from the Status columns.
6. Capture LO4 metrics | On the Protocol sheet: task success, time on task, satisfaction 1–5.
7. Sign-off | Product Owner and QA Lead complete the Dashboard sign-off (Accept / Accept with reservations / Reject).
STATUS LEGEND / IBISOBANURO
Pass | Test executed and all expected results were observed.
Fail | Test executed but one or more expected results did not match.
Blocked | Cannot be executed because of an environment/data/dependency issue.
Not Executed | Default — test case has not yet been run.
© Isoko / [Team name] — [Module code] capstone. Internal QA workbook. Do not distribute customer data.

## UAT Protocol
UAT Protocol / LO4 §2 — objectives, metrics, sign-off
This sheet is the formal UAT report skeleton required by the capstone module (LO4). Test evidence lives on the module sheets; the verdict lives here and on Dashboard.
2.1 Objectives
O1 A first-time buyer can register, browse products and complete a successful MoMo checkout unaided.
O2 Discount code SUMMER2026 and the qty≥5 / free-shipping decision table behave as SRS Appendix A.
O3 A mobile-money timeout never leaves an order Paid (FR-PAY-04 / FR-CHK-10).
O4 A seller can publish a product and ship a Paid order from the quick-start guide alone; payout is released only after OTP delivery.
O5 IDOR: buyer A cannot open buyer B’s order.
2.2 Metrics (complete during sessions)
Task (maps to objective) | Participant | Success Y/N | Time on task (min) | Satisfaction 1–5 | Notes
O1 Browse → register → MoMo success checkout
O2 Apply SUMMER2026 on 5× PC-500; Gold free shipping
O3 Force MoMo timeout; confirm not Paid
O4 Seller publish SKU + ship Paid order (quick-start only)
O5 Buyer A opens Buyer B order URL
Task success rate
Average satisfaction
Defects found in UAT (count of Fail on Dashboard) | 0
2.3 Participants (representative users, not only developers)
Name | Role | Session 1 / 2 | Trained on quick-start?
| Buyer (Buyer A, Standard) | 1
| Buyer (Gold / Buyer B) | 1
| Isoko Seller / Ops | 1+2
| Product Owner | 2 (sign-off)
| QA Lead | 1+2 | n/a
2.5–2.6 Verdict
Overall verdict
Reservations / conditions for go-live

## Dashboard
UAT Dashboard / Ipimo ry'ibyageragejwe
Live counts of Pass / Fail / Blocked / Not Executed across all test sheets. Do not type in the count cells.
Module | Pass | Fail | Blocked | Not Executed | Total | Pass rate
Authentication | 0 | 0 | 0 | 12 | 12 | 0%
Catalogue | 0 | 0 | 0 | 10 | 10 | 0%
Cart & Discount | 0 | 0 | 0 | 14 | 14 | 0%
Checkout | 0 | 0 | 0 | 14 | 14 | 0%
Wishlist & Orders | 0 | 0 | 0 | 14 | 14 | 0%
Seller & Admin | 0 | 0 | 0 | 8 | 8 | 0%
Non-functional | 0 | 0 | 0 | 10 | 10 | 0%
OVERALL | 0 | 0 | 0 | 82 | 82 | 0%
UAT SIGN-OFF / KWEMEZA
Role | Name | Decision | Signature | Date
Product Owner, Isoko
QA Lead
Trainer / Technical authority
Sign-off authorises (or refuses) release to the integrated summative demo / production-like cluster. It is not a developer “done”.

## Authentication
Authentication / Kwinjira
Login, lock-out, registration with phone OTP, session and logging. Maps to UC-01/02 and FR-AUTH-*.
Total | 12 | Pass | 0 | Fail | 0 | Blocked | 0 | Not Executed | 12 | Pass rate | 0%
# | Test ID | Module | Sub-module | Test Case Title | Pre-conditions | Test Steps | Expected Result | Actual Result | Priority | Status | Tester | Test Date | Defect ID | Comments
1 | AU-001 | Authentication | Welcome | Login page loads (smoke) | UAT cluster healthy. | Open /login. | Email and password fields and Sign in button are visible; labelled for assistive tech. |  | Critical | Not Executed |  |  |  | UC-02 / FR-AUTH-01
2 | AU-002 | Authentication | Happy path | Registered buyer logs in | amina@isoko.test exists (Appendix B). | 1. Open /login. 2. Enter amina@isoko.test + correct password. 3. Submit. | Redirect to previous page or home; session cookie set; user menu shows the email. |  | Critical | Not Executed |  |  |  | UC-02 main flow
3 | AU-003 | Authentication | Invalid password | Wrong password — generic error | amina@isoko.test exists. | Submit correct email + wrong password. | Generic error; no stack trace; does not say “password incorrect” vs “email unknown”. |  | Critical | Not Executed |  |  |  | UC-02 3a / FR-AUTH-03
4 | AU-004 | Authentication | Unknown email | Unknown email — same generic error | Email not in store. | Submit nobody@isoko.test + any password. | Same generic error as AU-003 (no user enumeration). |  | High | Not Executed |  |  |  | FR-AUTH-03
5 | AU-005 | Authentication | Lock-out | Account locks after 3 wrong passwords | Fresh failed-attempt counter. | Submit a wrong password three times in a row for amina@. | Third attempt locks 30 min; security notification requested; further logins denied. |  | Critical | Not Executed |  |  |  | FR-AUTH-04
6 | AU-006 | Authentication | Locked user | Already-locked account cannot log in | locked@isoko.test is locked. | Submit the correct password for the locked user. | Denied; message does not confirm the email exists. |  | High | Not Executed |  |  |  | FR-AUTH-05
7 | AU-007 | Authentication | Blank password | Blank password client validation | Login form. | Fill email, leave password empty, click Sign in. | “password is required” shown; no request sent. |  | Medium | Not Executed |  |  |  | FR-AUTH-01 form validation
8 | AU-008 | Authentication | Register | Register — happy path with phone OTP | New unique email; SMS stub returns OTP. | Complete register with valid 07X phone and 8+ char password (letter + digit); enter the SMS OTP. | Account activated only after OTP; user signed in; welcome message requested. |  | High | Not Executed |  |  |  | UC-01 / FR-AUTH-08, 09
9 | AU-009 | Authentication | Register | Register — duplicate email | amina@isoko.test already exists. | Register with amina@isoko.test. | Rejected; offer Log in; no second account. |  | High | Not Executed |  |  |  | UC-01 2a / FR-AUTH-10
10 | AU-010 | Authentication | Logging | Password never appears in logs | Access to API logs. | Run AU-002; inspect logs for the password string. | Logs show inputLen only; password absent. |  | High | Not Executed |  |  |  | FR-AUTH-07
11 | AU-011 | Authentication | Logout | Logout invalidates session | Logged in. | Logout; press Back; open /account. | Redirected to login; old cookie unusable. |  | High | Not Executed |  |  |  | FR-AUTH-11
12 | AU-012 | Authentication | Phone BVA | Register rejects 9-digit phone | Registration form. | Enter 078123456 (9 digits) as phone. | Rejected (Rwandan 07X 10-digit rule). |  | Medium | Not Executed |  |  |  | UC-01 2c / FR-AUTH-08

## Catalogue
Catalogue / Urutonde rw'ibicuruzwa
Smoke, search, published vs hidden, stock badges and product API. Maps to UC-03/04 and FR-CAT-*.
Total | 10 | Pass | 0 | Fail | 0 | Blocked | 0 | Not Executed | 10 | Pass rate | 0%
# | Test ID | Module | Sub-module | Test Case Title | Pre-conditions | Test Steps | Expected Result | Actual Result | Priority | Status | Tester | Test Date | Defect ID | Comments
1 | CAT-001 | Catalogue | Smoke | Home page loads | UAT up. | GET / | Home renders with at least the published catalogue region. If this fails, stop the cycle. |  | Critical | Not Executed |  |  |  | FR-CAT-04 smoke gate
2 | CAT-002 | Catalogue | List | Published products listed with RWF prices | TS-001 seeded. | Open the catalogue. | TS-001 visible; price 8,000 RWF (integer). |  | High | Not Executed |  |  |  | FR-CAT-01
3 | CAT-003 | Catalogue | Search | Search by name — hit | TS-001 published. | Search “T-shirt”. | TS-001 in results. |  | High | Not Executed |  |  |  | FR-CAT-02
4 | CAT-004 | Catalogue | Search | Search — zero hits empty state | None. | Search “zzzz-no-sku”. | “No products match your search.” — not a blank page. |  | Medium | Not Executed |  |  |  | UC-03 2a
5 | CAT-005 | Catalogue | Unpublished | Unpublished SKU hidden from guest | HIDDEN-01 unpublished. | Search HIDDEN-01 and open /p/HIDDEN-01. | Not in search; detail is 404. |  | High | Not Executed |  |  |  | FR-CAT-03, 06
6 | CAT-006 | Catalogue | Detail | Product detail in-stock | TS-001 stockQty=20. | Open the product. | Add to cart enabled; stock badge shows in stock. |  | High | Not Executed |  |  |  | UC-04
7 | CAT-007 | Catalogue | Detail | Out-of-stock disables add | BK-010 stockQty=0. | Open BK-010. | Add to cart and wishlist disabled. |  | High | Not Executed |  |  |  | FR-CAT-07
8 | CAT-008 | Catalogue | API | Unknown product id returns 404 | API reachable. | GET /v1/products/does-not-exist | HTTP 404 JSON with code and traceId; no stack trace. |  | High | Not Executed |  |  |  | FR-CAT-05
9 | CAT-009 | Catalogue | Health | /healthz ready for smoke | Cluster up. | GET /healthz and /readyz | 200; does not dump library versions. |  | High | Not Executed |  |  |  | DEV-09
10 | CAT-010 | Catalogue | Pagination | Catalogue paginates at 20 | More than 20 published products (seed extra if needed). | Open page 1 then page 2. | 20 items on page 1; remainder on page 2. |  | Medium | Not Executed |  |  |  | FR-CAT-02

## Cart & Discount
Cart & Discount / Agatebo n'igabanuka
Cart merge, EP/BVA on discount codes, 10% qty rule, shipping decision table. Maps to UC-05/06 and FR-CART-* / FR-DISC-* / FR-SHIP-01.
Total | 14 | Pass | 0 | Fail | 0 | Blocked | 0 | Not Executed | 14 | Pass rate | 0%
# | Test ID | Module | Sub-module | Test Case Title | Pre-conditions | Test Steps | Expected Result | Actual Result | Priority | Status | Tester | Test Date | Defect ID | Comments
1 | CART-001 | Cart | Add | Add in-stock item to cart | TS-001 in stock. | Add qty 1 from the product page. | Cart shows 1 × TS-001; confirmation shown. |  | Critical | Not Executed |  |  |  | UC-05 / FR-CART-01
2 | CART-002 | Cart | Qty | Qty greater than stock rejected | TS-001 stockQty=20. | Add qty 21. | Rejected; remaining 20 shown; cart unchanged. |  | High | Not Executed |  |  |  | FR-CART-02
3 | CART-003 | Cart | Merge | Anonymous cart merges on login | Guest cart has PC-500. | Log in as amina@isoko.test. | Cart retained; no duplicate SKU lines. |  | High | Not Executed |  |  |  | FR-CART-03
4 | CART-004 | Cart | Totals | Line totals = qty × unit price | 2 × PC-500 (5,000) in cart. | Open the cart. | Subtotal 10,000 RWF before shipping/discount. |  | High | Not Executed |  |  |  | FR-CART-04
5 | CART-005 | Discount | EP P1 | Code length 4 rejected | Cart non-empty. | Apply AB12. | “code must be 5–10 characters”; totals unchanged. |  | High | Not Executed |  |  |  | FR-DISC-02 / Appendix A.1
6 | CART-006 | Discount | EP P2 | Valid 10-character code accepted | Active code SUMMER2026. | Apply SUMMER2026. | Applied per remaining rules; not a length error. |  | High | Not Executed |  |  |  | FR-DISC-01 / upper boundary
7 | CART-007 | Discount | EP P3 | Code length 18 rejected | Cart non-empty. | Apply SUMMER2026BIGSALE1. | Length error; totals unchanged. |  | High | Not Executed |  |  |  | FR-DISC-02
8 | CART-008 | Discount | EP P4 | Non-alphanumeric code rejected | Cart non-empty. | Apply SAVE-25!. | “code contains invalid characters”. |  | High | Not Executed |  |  |  | FR-DISC-03
9 | CART-009 | Discount | BVA | Length 5 accepted / 11 rejected | Active 5-char code SAVE5 seeded. | Try SAVE5, then SAVE5678901 (11 chars). | 5 accepted structurally; 11 rejected. |  | High | Not Executed |  |  |  | FR-DISC-01, 02
10 | CART-010 | Discount | Unknown | Unknown code does not reduce price | Cart 10,000. | Apply FAKE99. | “code is not valid”; total unchanged. |  | High | Not Executed |  |  |  | FR-DISC-04
11 | CART-011 | Discount | Qty rule | 5 items get 10% off | PC-500 stock ≥ 5. | Set qty 5; no code applied. | Item subtotal 5 × 5,000 × 0.9 = 22,500. |  | High | Not Executed |  |  |  | FR-DISC-05
12 | CART-012 | Discount | Qty rule | 4 items get 0% off | PC-500 stock ≥ 4. | Set qty 4. | Subtotal 20,000; no 10% discount. |  | High | Not Executed |  |  |  | FR-DISC-05 boundary
13 | CART-013 | Shipping | Decision table | Standard buyer under 50k pays 2,500 home delivery (Kigali) | eric.buyer@isoko.test Standard; subtotal 10,000. | Open the checkout invoice (home delivery, Kigali). | Shipping 2,500 RWF. |  | High | Not Executed |  |  |  | FR-SHIP-01 / Appendix A.3 R4
14 | CART-014 | Shipping | Decision table | Gold buyer under 50k gets free shipping | gold@isoko.test; subtotal 10,000. | Open the checkout invoice as Gold. | Shipping 0 RWF. |  | High | Not Executed |  |  |  | Appendix A.3 R2

## Checkout
Checkout / Kwishyura
Place order, MoMo/Airtel/Card, escrow, timeout-after-Paid, idempotency, per-shop split. Maps to UC-07/08 and FR-CHK-* / FR-PAY-*.
Total | 14 | Pass | 0 | Fail | 0 | Blocked | 0 | Not Executed | 14 | Pass rate | 0%
# | Test ID | Module | Sub-module | Test Case Title | Pre-conditions | Test Steps | Expected Result | Actual Result | Priority | Status | Tester | Test Date | Defect ID | Comments
1 | CO-001 | Checkout | Gate | Checkout requires login | Guest cart non-empty. | Click Checkout. | Include::LOGIN; after success return to checkout. |  | Critical | Not Executed |  |  |  | UC-07 / FR-CHK-01
2 | CO-002 | Checkout | Empty | Empty cart cannot place order | Logged in, empty cart. | POST place order or click Pay. | Rejected; no order row. |  | High | Not Executed |  |  |  | FR-CHK-09
3 | CO-003 | Checkout | Happy MoMo | MoMo success → Paid, escrow held | amina@ cart valid; stub set to success. | Checkout → MTN MoMo → approve. | “transaction successful” with order number; Order=Paid; payment=held (escrow); notification requested; stock committed. |  | Critical | Not Executed |  |  |  | UC-08 main / FR-PAY-06
4 | CO-004 | Checkout | Happy Card | Card success → Paid | Stub set to success. | Checkout → Card → confirm. | Paid; card number not stored (inspect DB/payload). |  | High | Not Executed |  |  |  | FR-PAY-07
5 | CO-005 | Payment | Decline | Declined payment — buyer not charged | Stub set to decline. | Confirm pay. | Error displayed; order stays Placed; no Paid order; money = 0. |  | Critical | Not Executed |  |  |  | FR-CHK-06
6 | CO-006 | Checkout | Cancel | Buyer cancels before pay | On the invoice step. | Click Cancel and confirm “are you sure?”. | Back to cart; no order; no charge. |  | High | Not Executed |  |  |  | UC-07 *a
7 | CO-007 | Checkout | Idempotency | Double submit does not double charge | Stub set to success. | Double-click Place order / replay the Idempotency-Key. | One order, one charge. |  | High | Not Executed |  |  |  | FR-CHK-05
8 | CO-008 | Payment | Timeout | 45 s no callback → PaymentTimedOut, not Paid | Stub set to timeout. | Start MoMo pay; wait past 45 s. | State PaymentTimedOut; buyer not charged; message to retry. |  | Critical | Not Executed |  |  |  | FR-PAY-04
9 | CO-009 | Payment | Timeout after Paid | Late timeout after provisional Paid is corrected | Stub: success then timeout signal. | Complete pay; inject timeout/cancel from the stub. | Order leaves Paid → PaymentTimedOut/reconciled; ops alert; stock and money consistent. |  | Critical | Not Executed |  |  |  | FR-CHK-10
10 | CO-010 | Payment | Webhook | Duplicate or forged callback is ignored | Order already Paid. | 1. Replay the success webhook. 2. Send one with a wrong HMAC. | Still one Paid order, no second capture; forged callback rejected, state unchanged. |  | High | Not Executed |  |  |  | FR-PAY-03, 05
11 | CO-011 | Checkout | 10 minute abandon | Unpaid order is cancelled after 10 minutes | Order Placed, not paid. | Wait 10+ minutes (or trigger the job). | Order Cancelled; reserved stock available again. |  | Medium | Not Executed |  |  |  | FR-CHK-07, CART-05
12 | CO-012 | Checkout | OOS race | Last item bought by two buyers | LIM-001 stockQty=1; two sessions. | Both attempt checkout. | Only one Paid; the other sees a stock error; no oversell. |  | High | Not Executed |  |  |  | FR-CHK-09
13 | CO-013 | Checkout | Invoice | Invoice shows subtotal, shipping, discount, total | Cart with SUMMER2026 and a shipping rule. | Reach the invoice step. | Four figures visible in RWF; match FR-CART-04 rules. |  | High | Not Executed |  |  |  | FR-CHK-03
14 | CO-014 | Checkout | Multi-vendor | Cart with two shops is split per shop | Cart has TS-001 (Eric Fashion) and BK-020 (Kigali Books, in stock). | Check out and pay. | One order with two shop groups; each seller sees only their items. |  | High | Not Executed |  |  |  | FR-CHK-04

## Wishlist & Orders
Wishlist & Orders / Ibyifuzo n'ibitumwa
FR-WL-01..05 including persistence, IDOR, cancel-refund, legal and illegal order transitions. Maps to UC-09/10 and FR-ORD-*.
Total | 14 | Pass | 0 | Fail | 0 | Blocked | 0 | Not Executed | 14 | Pass rate | 0%
# | Test ID | Module | Sub-module | Test Case Title | Pre-conditions | Test Steps | Expected Result | Actual Result | Priority | Status | Tester | Test Date | Defect ID | Comments
1 | WO-001 | Wishlist | Add | Add in-stock item (FR-WL-01) | Logged in as amina@; TS-001 in stock. | Click Save to wishlist. | Item on the wishlist page. |  | High | Not Executed |  |  |  | UC-09
2 | WO-002 | Wishlist | OOS | Cannot add out-of-stock (FR-WL-02) | BK-010 out of stock. | Save to wishlist. | Rejected with message. |  | High | Not Executed |  |  |  | FR-WL-02
3 | WO-003 | Wishlist | Auth | Guest wishlist redirects to login | Logged out. | Open /wishlist. | Redirect to login; after login return to the wishlist. |  | High | Not Executed |  |  |  | UC-09 1b
4 | WO-004 | Wishlist | Icon | Icon updates without full refresh (FR-WL-03) | Logged in on a product page. | Add to wishlist; watch the icon. | Icon/count updates immediately. |  | High | Not Executed |  |  |  | FR-WL-03
5 | WO-005 | Wishlist | Cart | Move wishlist item to cart (FR-WL-05) | Item on the wishlist. | Move to cart. | Cart has the SKU. |  | Medium | Not Executed |  |  |  | FR-WL-05
6 | WO-006 | Wishlist | Persist | Wishlist persists across sessions (FR-WL-04) | Item saved. | Logout, login, open the wishlist. | Item still present. This case MUST stay on the RTM. |  | Critical | Not Executed |  |  |  | FR-WL-04
7 | WO-007 | Wishlist | Unpublished | Unpublished product cannot stay actionable | Seller unpublishes a wishlisted SKU. | Open the wishlist. | Item marked unavailable; move-to-cart disabled. |  | Medium | Not Executed |  |  |  | FR-CAT-03
8 | WO-008 | Orders | Track | Buyer sees own Paid order | CO-003 succeeded. | Open My orders. | Order number, Paid, lines by shop visible. |  | High | Not Executed |  |  |  | UC-10 / FR-ORD-03
9 | WO-009 | Orders | IDOR | Buyer A cannot read Buyer B's order | Two buyers with orders. | As A, GET /v1/orders/{B.id} and open B's URL. | 404 (not 403 with body leak). |  | Critical | Not Executed |  |  |  | FR-ORD-01 / SEC-04
10 | WO-010 | Orders | State | Legal path Placed→Paid→Shipped→Delivered | A Paid order; seller and agent accounts. | Seller ships with tracking; agent enters the delivery OTP. | Each transition succeeds; notifications requested; payout follows Delivered. |  | High | Not Executed |  |  |  | FR-ORD-02, 06, 07
11 | WO-011 | Orders | Illegal | Reject Delivered → Placed | Delivered order. | PATCH state=Placed. | HTTP 409 (ORD-409); state unchanged. |  | High | Not Executed |  |  |  | FR-ORD-02
12 | WO-012 | Orders | Cancel | Cancel a Paid order before shipping → refunded | Paid order, not yet Shipped. | Buyer cancels the order. | Order Refunded; full refund to the original method; stock released. |  | High | Not Executed |  |  |  | FR-ORD-04 / FR-PAY-10
13 | WO-013 | Orders | Illegal | Reject shipping an unpaid Placed order | Placed, unpaid order. | Seller marks Shipped. | Rejected; stays Placed. |  | High | Not Executed |  |  |  | UC-13 3a
14 | WO-014 | Orders | Unknown | Unknown order id is 404 | Logged in. | Open /orders/no-such-id. | 404. |  | Medium | Not Executed |  |  |  | FR-ORD-01

## Seller & Admin
Seller & Admin / Abacuruzi n'ubuyobozi
Authorisation, seller onboarding, listings, shipping with OTP, payout release, quick-start validation task (LO4). Maps to UC-11..14 and FR-SEL-* / FR-ADM-*.
Total | 8 | Pass | 0 | Fail | 0 | Blocked | 0 | Not Executed | 8 | Pass rate | 0%
# | Test ID | Module | Sub-module | Test Case Title | Pre-conditions | Test Steps | Expected Result | Actual Result | Priority | Status | Tester | Test Date | Defect ID | Comments
1 | SA-001 | Admin | Authz | Buyer cannot open admin console or seller API | amina@ is a buyer. | GET /admin and POST /v1/seller/products. | 403 / redirect; no product created. |  | Critical | Not Executed |  |  |  | FR-ADM-01 / SEC-04
2 | SA-002 | Seller | Onboarding | Admin approves a seller before publishing | newseller@isoko.test applied with an ID document. | 1. Seller tries to publish (blocked). 2. Admin approves. 3. Seller publishes. | Publish blocked until approval; approval notification sent; publish then succeeds. |  | Critical | Not Executed |  |  |  | UC-11 / FR-SEL-01..04
3 | SA-003 | Seller | Publish | Seller publishes a unique SKU | seller@isoko.test approved. | Create BAG-300, published, price 15,000, stock 5. | Appears on the storefront within 5 s. |  | High | Not Executed |  |  |  | UC-12 / FR-CAT-08
4 | SA-004 | Seller | Duplicate | Duplicate SKU rejected | TS-001 exists in the shop. | Create another TS-001. | Validation error; original unchanged. |  | High | Not Executed |  |  |  | FR-SEL-06
5 | SA-005 | Seller | Stock / price | Negative stock or zero price rejected | Seller on BAG-300. | Set stockQty=-1, then price=0. | Both rejected. |  | High | Not Executed |  |  |  | FR-SEL-07
6 | SA-006 | Seller | Ship | Seller ships a Paid order with tracking | A Paid order for the seller. | Enter tracking number; click Mark shipped. | State=Shipped; buyer gets a single-use delivery OTP. |  | High | Not Executed |  |  |  | UC-13 / FR-SEL-09, FR-ORD-06
7 | SA-007 | Seller | Payout | OTP delivery releases payout net of commission | Shipped order for 1 × TS-001 (8,000 RWF). | Agent enters the buyer's OTP. | State=Delivered; seller payout 7,200 RWF (8,000 − 8 % commission − 2 % fee); recorded in ledger. |  | Critical | Not Executed |  |  |  | UC-14 / FR-PAY-09
8 | SA-008 | Seller | Quick-start | Seller completes publish + ship using only the quick-start | O4 participant is not the feature's developer. | Hand over only the quick-start guide; time the task. | Task success without developer help; time recorded on the Protocol sheet. |  | High | Not Executed |  |  |  | LO4 UAT objective — validation, not verification

## Non-functional
Non-functional / Imikorere n'umutekano
Performance, pipeline, containers, security scans, observability and accessibility. Maps to NFR-* / SEC-* / DEV-*.
Total | 10 | Pass | 0 | Fail | 0 | Blocked | 0 | Not Executed | 10 | Pass rate | 0%
# | Test ID | Module | Sub-module | Test Case Title | Pre-conditions | Test Steps | Expected Result | Actual Result | Priority | Status | Tester | Test Date | Defect ID | Comments
1 | NF-001 | Non-functional | Perf | Login p95 ≤ 500 ms at 100 concurrent | JMeter/k6 script; UAT cluster. | Ramp 100 users logging in. | p95 ≤ 500 ms; error rate < 1 %. |  | High | Not Executed |  |  |  | NFR-PERF-03
2 | NF-002 | Non-functional | Load | 50 concurrent checkouts for 60 s, error rate < 1 % | k6 script. | 50 users for 60 s against the checkout API. | Error rate < 1 %; report attached. |  | High | Not Executed |  |  |  | NFR-PERF-04
3 | NF-003 | Non-functional | Stress | 200 concurrent fails gracefully | Stress script. | 200 concurrent checkouts. | No paid-without-stock; no HTML 500 stack traces; pods scale (HPA). |  | Medium | Not Executed |  |  |  | NFR-REL-02 / NFR-SCL-01
4 | NF-004 | Non-functional | Pipeline | CI test stage blocks a failing unit test | Repo with Jest tests. | Push a failing unit test on a branch. | Pipeline red; deploy did not run; merge blocked. |  | High | Not Executed |  |  |  | DEV-03, 04
5 | NF-005 | Non-functional | Security | Dependency and image scan gate | Pipeline configured. | Open the pipeline log; add a HIGH-severity test dependency. | Audit and Trivy steps present; HIGH finding fails the build. |  | High | Not Executed |  |  |  | SEC-11
6 | NF-006 | Non-functional | Containers | docker compose up is healthy in ≤ 3 minutes | Clean machine with Docker. | Run docker compose up; then docker compose ps. | Web, API, database, Redis, RabbitMQ healthy with seed data in ≤ 3 minutes. |  | High | Not Executed |  |  |  | DEV-01, 02
7 | NF-007 | Non-functional | Logs | JSON logs include trace_id | Hit /v1/products. | Read API stdout / Loki. | One JSON object per line with trace_id; no passwords or OTPs. |  | High | Not Executed |  |  |  | DEV-09 / NFR-LOG-01
8 | NF-008 | Non-functional | Dashboard | Grafana shows the four golden signals | Monitoring stack deployed. | Open the dashboard. | Latency, traffic, errors and saturation panels with live data. |  | High | Not Executed |  |  |  | DEV-10 / SLOs 8.2
9 | NF-009 | Non-functional | Alert | Checkout-success alert reaches the channel | Alert rule + Slack/e-mail webhook. | Force payment failures below the 95 % threshold. | Notification received; evidence attached. |  | High | Not Executed |  |  |  | SLO checkout success
10 | NF-010 | Non-functional | A11y | Checkout keyboard-only | Browser, no mouse. | Tab through checkout; complete with the keyboard. | All controls reachable; labels announced. |  | Medium | Not Executed |  |  |  | NFR-ACC-01